## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-01 | Study stock market fundamentals and commonly used technical indicators | MUST HAVE | No dependency | Brindha V C | 3- Completed
S1 | S1 | US-02 | Study the concept of backtesting in trading strategies | MUST HAVE | No dependency | Brindha V C | 3- Completed
S2 | S2 | US-03 | Explore Python-based backtesting frameworks (backtesting.py, vectorbt) | MUST HAVE | US-02 | Brindha V C | 3- Completed
S2 | S2 | US-04 | Workflow creation and module goal document | MUST HAVE | US-03 | Brindha V C | 3- Completed
S2 | S2 | US-05 | Test sample historical data using backtesting.py | MUST HAVE | US-03 | Brindha V C | 3- Completed
S3 | S3 | US-06 | Analyze performance metrics returned by backtesting frameworks | MUST HAVE | US-05 | Brindha V C | 3- Completed
S3 | S3 | US-07 | Backtest ML-generated buy/sell signals using live or historical data | SHOULD HAVE | US-06 | Brindha V C | 3- Completed
S4 | S4 | US-08 | Explore market return calculation to establish baseline validation | SHOULD HAVE | US-07 | Brindha V C | 3- Completed
S4 | S4 | US-09 | Compare ML strategy performance with market returns using metrics and graphs | MUST HAVE | US-08 | Brindha V C | 3- Completed
S5 | S5 | US-10 | Integrate ML strategy with market returns for unified backtesting analysis | MUST HAVE | US-09 | Brindha V C | 3- Completed
S5 | S5 | US-11 | Design and finalize the backtesting engine to compute comparative performance metrics | MUST HAVE | US-10 | Brindha V C | 3- Completed
S6 | S6 | US-12 | Develop a FastAPI service to expose backtesting metrics and graph data | MUST HAVE | US-11 | Brindha V C | 3- Completed
S6 | S6 | US-13 | Test and validate the backtesting API with ML signal inputs to ensure accurate end-to-end execution | MUST HAVE | US-12 | Brindha V C | 3- Completed
S7 | S7 | US-14 | Design and implement alert conditions based on backtesting outcomes and ML signal confidence | MUST HAVE | US-13 | Brindha V C | 3- Completed
S7 | S7 | US-15 | Develop and validate an alert generation mechanism to notify when BUY/SELL signals via Email | MUST HAVE | US-14 | Brindha V C | 3- Completed
S8 | S8 | US-16 | Perform end-to-end validation of backtesting and alert workflow using multiple tickers | MUST HAVE | US-13,15 | Brindha V C | 3- Completed
S8 | S8 | US-17 | Refine and optimize the backtesting and alert logic based on observed results and document the final module behavior | MUST HAVE | US-16 | Brindha V C | 3- Completed
Note on F1: ====== ID#AAAByM1USwU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 166 | 44 | 51 | 41 | 26 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T1.1 | Study market fundamentals | 26-11-25 | 27-11-26 | Brindha V C | Learning | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-01 | T1.2 | Learn indicators (RSI, MACD etc.) | 28-11-25 | 29-11-25 | Brindha V C | Learning | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.1 | Study backtesting concepts | 30-11-25 | 2025-01-12 | Brindha V C | Learning | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T2.2 | Document understanding | 2025-02-12 | 2025-02-12 | Brindha V C | Documentation | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-03 | T3.1 | Explore backtesting.py | 2025-03-12 | 2025-04-12 | Brindha V C | Learning | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T3.2 | Explore vectorbt | 2025-05-12 | 2025-06-12 | Brindha V C | Learning | 3- Completed | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T4.1 | Workflow creation | 2025-07-12 | 2025-08-12 | Brindha V C | Design | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T5.1 | Run backtest on sample data | 2025-09-12 | 2025-09-12 | Brindha V C | Build | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-06 | T6.1 | Analyze backtesting metrics | 2025-10-12 | 2025-11-12 | Brindha V C | Analysis | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T7.1 | Integrate ML signals | 2025-12-12 | 14-12-25 | Brindha V C | Coding | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T7.2 | Validate ML backtest | 15-12-25 | 16-12-25 | Brindha V C | Unit Test | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-08 | T8.1 | Implement market return | 17-12-25 | 19-12-25 | Brindha V C | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T9.1 | Compare ML vs market | 20-12-25 | 22-12-25 | Brindha V C | Coding | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T9.2 | Plot graphs | 23-12-25 | 23-12-25 | Brindha V C | Build | 3- Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-10 | T10.1 | Integrate strategies | 24-12-25 | 26-12-25 | Brindha V C | Coding | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T11.1 | Refactor engine | 27-12-25 | 29-12-25 | Brindha V C | Analysis | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T11.2 | Validate engine | 30-12-25 | 30-12-25 | Brindha V C | Unit Test | 3- Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-12 | T12.1 | Build FastAPI endpoints | 31-12-25 | 2026-01-01 | Brindha V C | Build | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T13.1 | API testing | 2026-02-01 | 2026-04-01 | Brindha V C | Unit Test | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T13.2 | Fix bugs | 2026-05-01 | 2026-06-01 | Brindha V C | Analysis | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG
US-14 | T14.1 | Define alert rules | 2026-01-07 | 2026-01-08 | Brindha V C | Build | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T14.2 | Implement alert logic | 2026-01-09 | 2026-01-11 | Brindha V C | Coding | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T15.1 | Email integration | 2026-01-12 | 2026-01-12 | Brindha V C | Coding | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T15.2 | Test alerts | 13-01-26 | 13-01-26 | Brindha V C | Unit Test | 3- Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG
US-16 | T16.1 | Multi-ticker testing | 14-01-26 | 18-01-26 | Brindha V C | Unit Test | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-16 | T16.2 | Identify edge cases | 19-01-26 | 21-01-26 | Brindha V C | Analysis | 3- Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T17.1 | Optimize logic | 22-01-26 | 25-01-26 | Brindha V C | Analysis | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T17.2 | Documentation | 26-01-26 | 28-01-26 | Brindha V C | Documentation | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAAByM1USv8 Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAAByM1USvQ Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAAByM1USvo Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAAByM1USvs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAAByM1USwI Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAAByM1USvw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAAByM1USwM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAAByM1USwA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAAByM1USvg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAAByM1USvc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAAByM1USwE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAAByM1USvk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAAByM1USv0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAAByM1USvU Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAAByM1USv4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAAByM1USvY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAAByM1USwQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 26-11-2025 | Initial learning curve with backtesting concepts | Team discussion and reference material review
Sprint 1 | 28-11-2025 | Difficulty understanding framework components | Studied documentation and clarified during group review
Sprint 1 | 2025-01-12 | No major impediments | Continued planned learning activities
Sprint 2 | 2025-03-12 | Delay in accessing historical stock data | Adjusted data source settings
Sprint 2 | 2025-05-12 | Data inconsistencies found | Cleaned and filtered dataset
Sprint 2 | 2025-08-12 | No major impediments | Proceeded with preprocessing tasks
Sprint 3 | 2025-10-12 | Understanding strategy class structure | Reviewed examples and team discussion
Sprint 3 | 2025-12-12 | Signal logic required refinement | Iterative testing and validation
Sprint 3 | 15-12-2025 | No major impediments | Continued implementation
Sprint 4 | 17-12-2025 | Designing alert trigger conditions | Defined alert rules and thresholds through discussion
Sprint 4 | 19-12-2025 | Email notification configuration issues | Verified SMTP settings and tested sample alerts
Sprint 4 | 22-12-2025 | No major impediments | Continued alerts module integration
Sprint 5 | 24-12-2025 | Learning curve for advanced signals | Reviewed references and examples
Sprint 5 | 26-12-2025 | Integration complexity | Incremental implementation
Sprint 5 | 29-12-2025 | No major impediments | Proceeded with metric calculations
Sprint 6 | 31-12-2025 | Scheduling alert monitoring intervals | Implemented time-based alert checks
Sprint 6 | 2026-02-01 | Alert duplication during testing | Added validation to avoid repeated notifications
Sprint 6 | 2026-05-01 | No major impediments | Alerts module stabilized and verified
Sprint 7 | 2026-07-01 | Parameter optimization took longer | Reduced parameter combinations
Sprint 7 | 2026-09-01 | Performance variation observed | Re-ran backtests for validation
Sprint 7 | 2026-12-01 | No major impediments | Finalized optimized results
Sprint 8 | 14-01-2026 | Export format alignment issues | Adjusted output structure
Sprint 8 | 20-01-2026 | Final review still in progress | Identified gaps for completion
Sprint 8 | 28-01-2026 | Project closure activities pending | Completed PPT, demo video, and finalized documentation

## Retrospection
SL # | Sprint # | Start Date | End Date | Team Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 26-11-2025 | 2025-02-12 | Backtesting & Alerts | Spend more time understanding fundamentals before implementation | Rushing into coding without clarity | Team discussions and reference reading | Allocated more time for learning and clarification in next sprint
2 | Sprint 2 | 2025-03-12 | 2025-09-12 | Backtesting & Alerts | Early data validation | Ignoring minor data issues initially | Collaborative problem-solving | Added data checks before preprocessing
3 | Sprint 3 | 2025-10-12 | 16-12-2025 | Backtesting & Alerts | Break strategy logic into smaller tasks | Working on complex logic in one go | Incremental implementation | Task breakdown improved in planning
4 | Sprint 4 | 17-12-2025 | 23-12-2025 | Backtesting & Alerts | Regular review of backtest outputs | Delaying validation until end | Reviewing results with team | Added mid-sprint validation step
5 | Sprint 5 | 24-12-2025 | 30-12-2025 | Backtesting & Alerts | Designing alert conditions and trigger rules early | Overloading sprint with unrelated features | Step-by-step enhancement | Defined alert criteria and basic trigger logic
6 | Sprint 6 | 31-12-2025 | 2026-06-01 | Backtesting & Alerts | Integrating email notification workflow | Manual alert testing without logs | Visualization and analysis | Implemented alert logs and notification testing
7 | Sprint 7 | 2026-07-01 | 13-01-2026 | Backtesting & Alerts | Limit optimization parameters | Running excessive combinations | Performance validation | Reduced parameter search space
8 | Sprint 8 | 14-01-2026 | 28-01-2026 | Backtesting & Alerts | Final PPT preparation, demo video recording, and documentation | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission