## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Conduct comprehensive research on backtesting modules and core concepts to establish a strong theoretical foundation. | MUST HAVE | Youtube, Gemini AI | Sai Karthik Reddy Kuppireddy | 3- Completed
S1 | S1 | US-002 | Evaluate specific backtesting libraries (VectorBT vs Backtesting.py) to determine which fits my performance needs. | MUST HAVE | US-001 | Sai Karthik Reddy Kuppireddy | 3- Completed
S2 | S2 | US-003 | Implement a standalone Backtesting.py script so that I can understand its event-driven architecture. | MUST HAVE | US-002 | Sai Karthik Reddy Kuppireddy | 3- Completed
S2 | S2 | US-004 | Implement a standalone VectorBT script to utilize its vectorization for high-speed analysis. | MUST HAVE | US-003 | Sai Karthik Reddy Kuppireddy | 3- Completed
S3 | S3 | US-005 | Design a Hybrid Integration architecture so that I can leverage VectorBT for speed and Backtesting.py for detail. | MUST HAVE | US-004 | Sai Karthik Reddy Kuppireddy | 3- Completed
S3 | S3 | US-006 | Implement the strategy logic within this Hybrid framework to ensure signals are generated consistently across both engines. | MUST HAVE | US-005 | Sai Karthik Reddy Kuppireddy | 3- Completed
S4 | S4 | US-007 | Integrate live market data (via yfinance) into the hybrid engine so that the system tests on real-time conditions. | MUST HAVE | US-006 | Sai Karthik Reddy Kuppireddy | 3- Completed
S4 | S4 | US-008 | Validate the live data feed format to prevent data type errors during strategy execution. | SHOULD HAVE | US-007 | Sai Karthik Reddy Kuppireddy | 3- Completed
S5 | S5 | US-009 | Generate performance reports (Sharpe, Drawdown) from the Hybrid engine to analyze strategy success. | MUST HAVE | US-008 | Sai Karthik Reddy Kuppireddy | 3- Completed
S5 | S5 | US-010 | Fix dictionary KeyErrors (e.g., 'Total Return%') in the reporting module to ensure stable output. | MUST HAVE | US-009 | Sai Karthik Reddy Kuppireddy | 3- Completed
S6 | S6 | US-011 | Research various alert notification modules (e.g., SMTPLIB) for an automated email system requirements. | MUST HAVE | US-010 | Sai Karthik Reddy Kuppireddy | 3- Completed
S6 | S6 | US-012 | Define the specific triggering conditions (e.g., RSI levels, SMA crossovers) that will activate an alert notification. | SHOULD HAVE | US-011 | Sai Karthik Reddy Kuppireddy | 3- Completed
S7 | S7 | US-013 | Develop a script to send automated emails with trade signals and performance summaries to the user's inbox. | MUST HAVE | US-012 | Sai Karthik Reddy Kuppireddy | 3- Completed
S7 | S7 | US-014 | Integrate the alert system into the Hybrid Engine to ensure real-time notification based on live market data. | MUST HAVE | US-007,US-013 | Sai Karthik Reddy Kuppireddy | 3- Completed
S8 | S8 | US-015 | Conduct end-to-end testing of the alert system during high-volatility simulations to ensure email delivery is consistent. | MUST HAVE | US-014 | Sai Karthik Reddy Kuppireddy | 3- Completed
S8 | S8 | US-016 | Finalize the complete backtesting and alert system documentation to ensure it is ready for final project submission. | MUST HAVE | US-015 | Sai Karthik Reddy Kuppireddy | 3- Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 96 | 27 | 29 | 24 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | T1.1 | Research core backtesting concepts. | 2025-11-26 | 2025-11-27 | Sai Karthik Reddy Kuppireddy | Research | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | T1.2 | Benchmark VectorBT vs. Backtesting.py. | 2025-11-28 | 2025-11-29 | Sai Karthik Reddy Kuppireddy | Analysis | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-003 | T2.1 | Implement Backtesting.py architecture. | 2025-12-02 | 2025-12-01 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | T2.2 | Develop standalone VectorBT script. | 2025-12-05 | 2025-12-02 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-005 | T3.1 | Architect dual-engine hybrid system. | 2025-12-09 | 2025-12-04 | Sai Karthik Reddy Kuppireddy | Analysis | 3- Completed | 5 | 1 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | T3.2 | Code strategy logic for engine consistency. | 2025-12-12 | 2025-12-06 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-007 | T4.1 | Integrate real-time yfinance API. | 2025-12-16 | 2025-12-08 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | T4.2 | Validate data feed formats and types. | 2025-12-19 | 2025-12-09 | Sai Karthik Reddy Kuppireddy | Testing | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-009 | T5.1 | Generate Sharpe and Drawdown reports. | 2025-12-23 | 2025-12-12 | Sai Karthik Reddy Kuppireddy | Analysis | 3- Completed | 5 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | T5.2 | Debug reporting module KeyErrors. | 2025-12-30 | 2025-12-13 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 6 BACKLOG
US-011 | T6.1 | Research SMTPLIB and email protocols. | 2026-01-05 | 2025-12-15 | Sai Karthik Reddy Kuppireddy | Research | 3- Completed | 6 | 1 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | T6.2 | Define RSI and SMA trigger logic. | 2026-01-08 | 2025-12-17 | Sai Karthik Reddy Kuppireddy | Analysis | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 7 BACKLOG
US-013 | T7.1 | Develop automated email notification scripts. | 2026-01-13 | 2025-12-19 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | T7.2 | Integrate alert system with Hybrid Engine. | 2026-01-16 | 2025-12-21 | Sai Karthik Reddy Kuppireddy | Development | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 8 BACKLOG
US-015 | T8.1 | Execute volatility stress tests on alerts. | 2026-01-21 | 2025-12-24 | Sai Karthik Reddy Kuppireddy | Testing | 3- Completed | 7 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | T8.2 | Finalize documentation and submission. | 2026-01-26 | 2025-12-27 | Sai Karthik Reddy Kuppireddy | Documentation | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US ID | Task ID | Task Description | Team Member | Activity | Status | Est (Hrs) | D1 | D2 | Day 1: D3; Day 2: D4; Day 3: D5; Day 4: D6–D14
US-001 | T1.1 | Research core backtesting concepts. | Sai Karthik Reddy | Research | Done | 8 | 4 | 4
US-002 | T1.2 | Benchmark VectorBT vs. Backtesting.py. | Sai Karthik Reddy | Analysis | Done | 12 |  |  | Day 1: 4; Day 2: 4; Day 3: 4
US-003 | T2.1 | Implement Backtesting.py architecture. | Sai Karthik Reddy | Development | Done | 12 | 4 | 4 | Day 1: 4
US-004 | T2.2 | Develop standalone VectorBT script. | Sai Karthik Reddy | Development | Done | 8 |  |  | Day 2: 4; Day 3: 4
US-005 | T3.1 | Architect dual-engine hybrid system. | Sai Karthik Reddy | Analysis | Done | 10 | 4 | 4 | Day 1: 2
US-006 | T3.2 | Code strategy logic for engine consistency. | Sai Karthik Reddy | Development | Done | 10 |  |  | Day 1: 2; Day 2: 4; Day 3: 4
US-007 | T4.1 | Integrate real-time yfinance API. | Sai Karthik Reddy | Development | Done | 12 | 4 | 4 | Day 1: 4
US-008 | T4.2 | Validate data feed formats and types. | Sai Karthik Reddy | Testing | Done | 8 |  |  | Day 2: 4; Day 3: 4
US-009 | T5.1 | Generate Sharpe and Drawdown reports. | Sai Karthik Reddy | Analysis | Done | 10 | 4 | 4 | Day 1: 2
US-010 | T5.2 | Debug reporting module KeyErrors. | Sai Karthik Reddy | Development | Done | 10 |  |  | Day 1: 2; Day 2: 4; Day 3: 4
US-011 | T6.1 | Research SMTPLIB and email protocols. | Sai Karthik Reddy | Research | Done | 6 | 3 | 3
US-012 | T6.2 | Define RSI and SMA trigger logic. | Sai Karthik Reddy | Analysis | Done | 10 |  |  | Day 1: 3; Day 2: 4; Day 3: 3
US-013 | T7.1 | Develop automated email notification scripts. | Sai Karthik Reddy | Development | Done | 12 | 4 | 4 | Day 1: 4
US-014 | T7.2 | Integrate alert system with Hybrid Engine. | Sai Karthik Reddy | Development | Done | 8 |  |  | Day 2: 4; Day 3: 4
US-015 | T8.1 | Execute volatility stress tests on alerts. | Sai Karthik Reddy | Testing | Done | 12 | 4 | 4 | Day 1: 4
US-016 | T8.2 | Finalize documentation and submission. | Sai Karthik Reddy | Documentation | Done | 8 |  |  | Day 2: 4; Day 3: 4

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 26-11-2025 | Initial learning curve with backtesting concepts | Team discussion and reference material review
Sprint 1 | 28-11-2025 | Difficulty understanding framework components | Studied documentation and clarified during group review
Sprint 1 | 2025-01-12 | No major impediments | Continued planned learning activities
Sprint 2 | 2025-03-12 | Delay in accessing historical stock data | Adjusted data source settings
Sprint 2 | 2025-05-12 | Data inconsistencies found | Cleaned and filtered dataset
Sprint 2 | 2025-08-12 | No major impediments | Proceeded with preprocessing tasks
Sprint 3 | 2025-10-12 | Understanding strategy class structure | Reviewed examples and team discussion
Sprint 3 | 2025-12-12 | Signal logic required refinement | Iterative testing and validation
Sprint 3 | 15-12-2025 | No major impediments | Continued implementation
Sprint 4 | 17-12-2025 | Designing alert trigger conditions | Defined alert rules and thresholds through discussion
Sprint 4 | 19-12-2025 | Email notification configuration issues | Verified SMTP settings and tested sample alerts
Sprint 4 | 22-12-2025 | No major impediments | Continued alerts module integration
Sprint 5 | 24-12-2025 | Learning curve for advanced signals | Reviewed references and examples
Sprint 5 | 26-12-2025 | Integration complexity | Incremental implementation
Sprint 5 | 29-12-2025 | No major impediments | Proceeded with metric calculations
Sprint 6 | 31-12-2025 | Scheduling alert monitoring intervals | Implemented time-based alert checks
Sprint 6 | 2026-02-01 | Alert duplication during testing | Added validation to avoid repeated notifications
Sprint 6 | 2026-05-01 | No major impediments | Alerts module stabilized and verified
Sprint 7 | 2026-07-01 | Parameter optimization took longer | Reduced parameter combinations
Sprint 7 | 2026-09-01 | Performance variation observed | Re-ran backtests for validation
Sprint 7 | 2026-12-01 | No major impediments | Finalized optimized results
Sprint 8 | 14-01-2026 | Export format alignment issues | Adjusted output structure
Sprint 8 | 20-01-2026 | Final review still in progress | Identified gaps for completion
Sprint 8 | 28-01-2026 | Project closure activities pending | Completed PPT, demo video, and finalized documentation

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 26-11-2025 | 2025-02-12 | Backtesting & Alerts Team | Spend more time understanding fundamentals before implementation | Rushing into coding without clarity | Team discussions and reference reading | Allocated more time for learning and clarification in next sprint
2 | Sprint 2 | 2025-03-12 | 2025-09-12 | Backtesting & Alerts Team | Early data validation | Ignoring minor data issues initially | Collaborative problem-solving | Added data checks before preprocessing
3 | Sprint 3 | 2025-10-12 | 16-12-2025 | Backtesting & Alerts Team | Break strategy logic into smaller tasks | Working on complex logic in one go | Incremental implementation | Task breakdown improved in planning
4 | Sprint 4 | 17-12-2025 | 23-12-2025 | Backtesting & Alerts Team | Regular review of backtest outputs | Delaying validation until end | Reviewing results with team | Added mid-sprint validation step
5 | Sprint 5 | 24-12-2025 | 30-12-2025 | Backtesting & Alerts Team | Designing alert conditions and trigger rules early | Overloading sprint with unrelated features | Step-by-step enhancement | Defined alert criteria and basic trigger logic
6 | Sprint 6 | 31-12-2025 | 2026-06-01 | Backtesting & Alerts Team | Integrating email notification workflow | Manual alert testing without logs | Visualization and analysis | Implemented alert logs and notification testing
7 | Sprint 7 | 2026-07-01 | 13-01-2026 | Backtesting & Alerts Team | Limit optimization parameters | Running excessive combinations | Performance validation | Reduced parameter search space
8 | Sprint 8 | 14-01-2026 | 28-01-2026 | Backtesting & Alerts Team | Final PPT preparation, demo video recording, and documentation | Leaving presentation and docs to last minute | Team collaboration | Completed PPT, demo video, final documentation, and project submission